## COB
| WIP | Fail |  | COB
WO | Qty In | Note | Fill Target Start Time, Input/Output, Machine Used, Actual Start/End, and Fail ONLY | RX DB |  | RX Baking |  | FSI DB |  | FSI Baking |  | TX-COS DB |  | Die Visual Inspection |  | Dimension Test |  | TX-COS Baking |  | COB WB |  | Die/Wire Inspection |  | Die/Wire Visual Inspection |  | TX Lens Coupling |  | COB Black Glue Fixing |  | COB Black Glue Baking |  | COB Visual Inspection |  | Yield
120011111 | 20 | NA | Target UPH | 16 |  | 248 |  | 51 |  | 248 |  | 23 |  | 60 |  | 60 |  | 248 |  | 32 |  | 16 |  | 60 |  | 4 |  | 40 |  | 248 |  | 60
|  |  | # Machine Used | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  |  | Expected Work Hours | 0.052083 |  | 0.083333 |  | 0.014706 |  | 0.083333 |  | 0.032609 |  | 0.010417 |  | 0.010417 |  | 0.083333 |  | 0.015625 |  | 0.015625 |  | 0.0041667 |  | 0.0625 |  | 0.00625 |  | 0.083333 |  | 0.0041667
|  |  | Target Start/End | 2026-05-05 09:00 | 2026-05-05 10:15 | 2026-05-05 10:00 | 2026-05-05 12:00 | 2026-05-05 09:00 | 2026-05-05 09:21 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:47 | 2026-05-05 09:00 | 2026-05-05 09:15 | 2026-05-05 09:00 | 2026-05-05 09:15 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:22 | 2026-05-05 09:00 | 2026-05-05 09:22 | 2026-05-05 09:00 | 2026-05-05 09:06 | 2026-05-05 09:00 | 2026-05-05 10:30 | 2026-05-05 09:00 | 2026-05-05 09:09 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:06
|  |  | Actual Start/End | 2026-05-05 09:15 | 2026-05-05 11:15
|  |  | Actual Work Hours | 0.083333 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | Actual UPH | 10 |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  | WO InputOut | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 5%
|  |  | WIP / Fail | 0 | 2 | 0 |  | 0 |  | 0 |  | 3 |  | -2 | 2 | 0 |  | 3 |  | 6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5
|  |  | Yield | 90% |  | 100% |  | 100% |  | 100% |  | 83.33% |  | 100% |  | 100% |  | 80% |  | 50% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 16.67%
120011112 | 20 | NA | Target UPH | 16 |  | 248 |  | 51 |  | 248 |  | 23 |  | 60 |  | 60 |  | 248 |  | 32 |  | 16 |  | 60 |  | 4 |  | 40 |  | 248 |  | 60
|  |  | # Machine Used | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  |  | Expected Work Hours | 0.052083 |  | 0.083333 |  | 0.01634 |  | 0.083333 |  | 0.036232 |  | 0.013889 |  | 0.013889 |  | 0.083333 |  | 0.026042 |  | 0.052083 |  | 0.013889 |  | 0.20833 |  | 0.020833 |  | 0.083333 |  | 0.013889
|  |  | Target Start/End | 2026-05-05 09:00 | 2026-05-05 10:15 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:24 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:52 | 2026-05-05 09:00 | 2026-05-05 09:20 | 2026-05-05 09:00 | 2026-05-05 09:20 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:38 | 2026-05-05 09:00 | 2026-05-05 10:15 | 2026-05-05 09:00 | 2026-05-05 09:20 | 2026-05-05 09:00 | 2026-05-05 14:00 | 2026-05-05 09:00 | 2026-05-05 09:30 | 2026-05-05 09:00 | 2026-05-05 11:00 | 2026-05-05 09:00 | 2026-05-05 09:20
|  |  | Actual Start/End | 2026-05-05 09:15 | 2026-05-05 11:15
|  |  | Actual Work Hours | 0.083333 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  | Actual UPH | 10 |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
|  |  | WO In/Out | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 90%
|  |  | WIP / Fail | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -2 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
|  |  | Yield by Station | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 90%
|  |  | Input/Output All WOs | 40 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 35 | 35 | 35 | 35 | 35 | 35 | 32 | 32 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 19 | 5%
|  |  | Yield by Station All WOs | 95% |  | 100% |  | 100% |  | 100% |  | 92.11% |  | 100% |  | 100% |  | 91.43% |  | 81.25% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 73.08%
Formulas:
COB = (E10/(E3*[COB, row above]))/24
COB = F7-[COB, row above]
RX Baking = H7-[RX Baking, row above]
FSI DB = (I10/(I3*[FSI DB, row above]))/24
FSI DB = J7-[FSI DB, row above]
FSI Baking = L7-[FSI Baking, row above]
TX-COS DB = (M10/(M3*[TX-COS DB, row above]))/24
TX-COS DB = N7-[TX-COS DB, row above]
Die Visual Inspection = (O10/(O3*[Die Visual Inspection, row above]))/24
Die Visual Inspection = P7-[Die Visual Inspection, row above]
Dimension Test = (Q10/(Q3*[Dimension Test, row above]))/24
Dimension Test = R7-[Dimension Test, row above]
TX-COS Baking = T7-[TX-COS Baking, row above]
COB WB = (U10/(U3*[COB WB, row above]))/24
COB WB = V7-[COB WB, row above]
Die/Wire Inspection = (W10/(W3*[Die/Wire Inspection, row above]))/24
Die/Wire Inspection = X7-[Die/Wire Inspection, row above]
Die/Wire Visual Inspection = (Y10/(Y3*[Die/Wire Visual Inspection, row above]))/24
Die/Wire Visual Inspection = Z7-[Die/Wire Visual Inspection, row above]
TX Lens Coupling = (AA10/(AA3*[TX Lens Coupling, row above]))/24
TX Lens Coupling = AB7-[TX Lens Coupling, row above]
COB Black Glue Fixing = (AC10/(AC3*[COB Black Glue Fixing, row above]))/24
COB Black Glue Fixing = AD7-[COB Black Glue Fixing, row above]
COB Black Glue Baking = AF7-[COB Black Glue Baking, row above]
COB Visual Inspection = (AG10/(AG3*[COB Visual Inspection, row above]))/24
COB Visual Inspection = AH7-[COB Visual Inspection, row above]

## Module Assembly (hidden)
100G | 200G | 400G |  | COB
WO | Qty In | Note | [43 empty] | Yield
120048945 | 20 | 100G | Target Date | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03
|  |  | Actual Date | [10 empty] | 2026-02-03 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12
|  |  | WO In/Out | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 90%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 90% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
|  |  |  | 20 | 20 | 20 | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 90%
|  |  |  | 100% |  | 100% |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Note on Y4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Burn-in machines issue
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 in repairs: S147244700032 S147244700032

## AOC 400G WOs (hidden)
100G | 200G | 400G |  | AOC
WO | Qty In | Note |  | Start Runcard |  | AOC Assembly All 1 |  | AOC Assembly All 2 |  | AOC Assembly All 3 |  | AOC Assembly 1 |  | AOC Assembly 2 |  | AOC Assembly 3 |  | AOC Baking |  | AOC 20TC |  | AOC Post Test |  | TCBer Test |  | Symbol Error Test |  | ATS Test |  | Packet Loss Test |  | AOC Inspection |  | INVT PCS |  | Yield
120049067 | 15 | 400G | Target Date | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05
|  |  | Actual Date | 2026-02-04 | [7 empty] | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-08 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-23
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 12 | 12 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 66.67%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 80% |  | 100% |  | 91.67% |  | 90.91% |  | 100% |  | 100% |  | 100%
120049068 | 15 | 400G | Target Date | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-06
|  |  | Actual Date | [14 empty] | 2026-02-05 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-23
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 66.67%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 80% |  | 91.67% |  | 100% |  | 90.91% |  | 100% |  | 100% |  | 100%
120049169 | 15 | 400G | Target Date | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-07
|  |  | Actual Date | [14 empty] | 2026-02-06 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-23
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 66.67%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 73.33% |  | 100% |  | 90.91% |  | 100% |  | 100% |  | 100% |  | 100%
120049170 | 15 | 400G | Target Date | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-09
|  |  | Actual Date | 2026-02-05 | [7 empty] | 2026-02-06 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-23
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 53.33%
|  |  | Yield | 100% |  | 100% |  | 73.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 72.73% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
120049430 | 30 | 400G | Target Date | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13
|  |  | Actual Date | 2026-02-09 | [7 empty] | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-24
|  |  | WO In/Out | 30 | 30 | 30 | 30 | 30 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 21 | 21 | 21 | 21 | 20 | 20 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 53.33%
|  |  | Yield | 100% |  | 100% |  | 86.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 80.77% |  | 100% |  | 95.24% |  | 80% |  | 100% |  | 100% |  | 100%
120049431 | 30 | 400G | Target Date | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-14
|  |  | Actual Date | 2026-02-09 | [7 empty] | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-24
|  |  | WO In/Out | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 24 | 24 | 24 | 24 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 40%
|  |  | Yield | 100% |  | 100% |  | 83.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 96% |  | 100% |  | 50% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
120049432 | 30 | 400G | Target Date | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16
|  |  | Actual Date | 2026-02-12 | [7 empty] | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-24
|  |  | WO In/Out | 30 | 30 | 30 | 30 | 30 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 20 | 20 | 18 | 18 | 16 | 16 | 14 | 14 | 13 | 13 | 12 | 12 | 12 | 40%
|  |  | Yield | 100% |  | 100% |  | 96.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 68.97% |  | 90% |  | 88.89% |  | 87.5% |  | 92.86% |  | 92.31% |  | 100%
120049433 | 30 | 400G | Target Date | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-17
|  |  | Actual Date | 2026-02-13 | [7 empty] | 2026-02-13 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-24
|  |  | WO In/Out | 30 | 30 | 30 | 30 | 30 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 26 | 26 | 26 | 26 | 20 | 20 | 17 | 17 | 16 | 16 | 14 | 14 | 4 | 4 | 4 | 4 | 4 | 13.33%
|  |  | Yield | 100% |  | 100% |  | 93.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 92.86% |  | 100% |  | 76.92% |  | 85% |  | 94.12% |  | 87.5% |  | 28.57% |  | 100% |  | 100%
120049434 | 30 | 400G | Target Date | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19
|  |  | Actual Date | 2026-02-16 | [7 empty] | 2026-02-16 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-24
|  |  | WO In/Out | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 19 | 19 | 17 | 17 | 17 | 17 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 40%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 63.33% |  | 89.47% |  | 100% |  | 70.59% |  | 100% |  | 100% |  | 100%
120049852 | 20 | 400G | Target Date | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23
|  |  | Actual Date | 2026-02-19 | [7 empty] | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-26 |  | 2026-02-27 |  | 2026-03-02 |  | 2026-03-04
|  |  | WO In/Out | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 18 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 10%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 90% |  | 44.44% |  | 100% |  | 100% |  | 25% |  | 100% |  | 100%
120049853 | 25 | 400G | Target Date | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-23
|  |  | Actual Date | 2026-02-19 |  | 2026-02-19 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-24 |  | 2026-03-25 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-02 |  | 2026-03-04 |  | 2026-03-04
|  |  | WO In/Out | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 18 | 18 | 11 | 11 | 7 | 7 | 7 | 7 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 8%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 72% |  | 61.11% |  | 63.64% |  | 100% |  | 57.14% |  | 75% |  | 66.67% |  | 100%
120050119 | 14 | 400G | Target Date | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-04 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05
|  |  | Actual Date | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11
|  |  | WO In/Out | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 10 | 8 | 8 | 7 | 7 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 14.29%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 71.43% |  | 80% |  | 87.5% |  | 42.86% |  | 100% |  | 66.67% |  | 100%
120050120 | 20 | 400G | Target Date | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06
|  |  | Actual Date | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11
|  |  | WO In/Out | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14 | 14 | 14 | 14 | 13 | 13 | 9 | 9 | 8 | 8 | 6 | 6 | 5 | 25%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 70% |  | 100% |  | 92.86% |  | 69.23% |  | 88.89% |  | 75% |  | 83.33%
120050202 | 10 | 400G | Target Date | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09
|  |  | Actual Date | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-11
|  |  | WO In/Out | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 60%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 70% |  | 100% |  | 100% |  | 85.71% |  | 100% |  | 100% |  | 100%
120050204 | 10 | 400G | Target Date | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10
|  |  | Actual Date | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-11
|  |  | WO In/Out | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 30%
|  |  | Yield | 100% |  | 100% |  | 70% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 85.71% |  | 100% |  | 83.33% |  | 100% |  | 100% |  | 60%
120050206 | 10 | 400G | Target Date | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12
|  |  | Actual Date | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17
|  |  | WO In/Out | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 4 | 4 |  | 0%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 80% |  | 100% |  | 87.5% |  | 85.71% |  | 100% |  | 66.67% |  | 0%
120050336 | 15 | 400G | Target Date | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-14
|  |  | Actual Date | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-17
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | [13 empty] | 0%
|  |  | Yield | 100% |  | 100% |  | 93.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 0% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
120050413 | 15 | 400G | Target Date | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13
|  |  | Actual Date | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 |  | 0%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 66.67% |  | 80% |  | 100% |  | 100% |  | 100% |  | 37.5% |  | 0%
120050414 | 15 | 400G | Target Date | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16
|  |  | Actual Date | 2026-03-11 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-16 |  | 2026-03-17
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 11 | 11 | [11 empty] | 0%
|  |  | Yield | 100% |  | 100% |  | 93.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 78.57% |  | 0% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
120050602 | 15 | 400G | Target Date | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17
|  |  | Actual Date | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-23 |  | 2026-03-23
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 4 | 26.67%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 93.33% |  | 100% |  | 100% |  | 92.86% |  | 69.23% |  | 88.89% |  | 100% |  | 100% |  | 100% |  | 62.5% |  | 80%
120050337 | 15 | 400G | Target Date | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-17
Actual Date
|  |  | WO In/Out | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | [16 empty] | #REF!
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
120050338 | 35 | 400G | Target Date | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-19
|  |  | Actual Date | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-23 |  | 2026-03-23
|  |  | WO In/Out | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 30 | 30 | 25 | 25 | 23 | 23 | 15 | 15 | 13 | 13 | 3 | 3 |  | 0%
|  |  | Yield | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 85.71% |  | 83.33% |  | 92% |  | 65.22% |  | 86.67% |  | 23.08% |  | 0%
|  |  |  | 429 | 429 | 429 | 429 | 429 | 408 | 408 | 408 | 408 | 408 | 408 | 407 | 407 | 407 | 407 | 404 | 389 | 381 | 381 | 270 | 270 | 226 | 226 | 215 | 215 | 178 | 178 | 157 | 157 | 132 | 132 | 118 | 38.25%
|  |  |  | 100% |  | 100% |  | 95.1% |  | 100% |  | 100% |  | 99.75% |  | 100% |  | 99.26% |  | 97.94% |  | 70.87% |  | 83.7% |  | 95.13% |  | 82.79% |  | 88.2% |  | 84.08% |  | 89.39%
Formulas:
AOC Assembly All 1 = WORKDAY.INTL([Start Runcard],0,11)
AOC Assembly All 2 = WORKDAY.INTL([AOC Assembly All 1],0,11)
AOC Assembly All 3 = WORKDAY.INTL([AOC Assembly All 2],0,11)
AOC Assembly 1 = WORKDAY.INTL([Start Runcard],0,11)
AOC Assembly 2 = WORKDAY.INTL([AOC Assembly 1],0,11)
AOC Assembly 3 = WORKDAY.INTL([AOC Assembly 2],0,11)
AOC Baking = WORKDAY.INTL([AOC Assembly 3],0,11)
AOC 20TC = WORKDAY.INTL([AOC Baking],0,11)
AOC Post Test = WORKDAY.INTL([AOC 20TC],2,11)
TCBer Test = WORKDAY.INTL([AOC Post Test],0,11)
Symbol Error Test = WORKDAY.INTL([TCBer Test],1,11)
ATS Test = WORKDAY.INTL([Symbol Error Test],0,11)
Packet Loss Test = WORKDAY.INTL([ATS Test],0,11)
AOC Inspection = WORKDAY.INTL([Packet Loss Test],0,11)
INVT PCS = WORKDAY.INTL([AOC Inspection],0,11)
Note on X5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9067260100001 9067260100002 9067260100008 Reply: scrapped
Note on AD5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: repair: 9067260100003
Note on AH5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 in repair: 9067260100012
Note on X9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 fails 9068260100012 9068260100015 Reply: scrapped
Note on AH9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 wip 3 fails 9068260100005 9068260100006 9068260100010
Note on X13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9169260200001 9169260200007 9169260200014 Reply: scrapped
Note on AB13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 repair: 9169260200003
Note on AH13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 wip 1 fails 9169260200012
Note on J17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: scrapped
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 wip Reply: scrapped
Note on X17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fail 9170260200001 9170260200004 9170260200007 Reply: scrapped
Note on AH17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 wip 1 fail 9170260200008
Note on J21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 scrapped
Note on X21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 scrapped
Note on AB21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 repair: 9430260200027
Note on J25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: scrapped
Note on T25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 scrapped
Note on X25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12 scrapped
Note on AF25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 wip @ asbl 2
Note on J29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: scrapped
Note on X29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8 scrapped
Note on AB29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: repair
Note on J33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 scrapped
Note on T33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 scrapped
Note on X33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 scrapped
Note on Z33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 wip 2 repairs
Note on AB33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 repair
Note on X37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 11 scrapped
Note on Z37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 repairs
Note on X41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 scrapped
Note on Z41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 repairs
Note on X45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 scrapped
Note on AH45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 repair
Note on X49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 repairs
Note on AH49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 repair
Note on X53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 repairs
Note on AH53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 repairs
Note on X57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: repair
Note on AH57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: repair
Note on J61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: scrapped 3
Note on AH65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 repairs: 0206260300001 0206260300005
Note on AH73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 repairs: 0413260300003 0413260300007 0413260300009 0413260300011 0413260300012
Note on AH81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 repairs: 0602260300004 0602260300008

## MSFT Orders Summary (hidden)
Process | Station | Input | Output | WIP | Repair | Fixed | Scrapped | FPY | Overall Yield
COB 100G & 200G | FW Writing | 40 | 38 | 2 | 0 |  | 0 | 100% | 100%
| Plasma Cleaning | 38 | 38 | 0 | 0 |  | 0 | 100% | 100%
| IC Die Bonding | 38 | 38 | 0 | 0 |  | 0 | 100% | 100%
| IC Size Check | 38 | 38 | 0 | 0 |  | 0 | 100% | 100%
| Baking H20S | 38 | 35 | 3 | 0 |  | 0 | 100% | 100%
| Wire Bonding | 35 | 35 | 2 | 12 |  | 12 | 71.43% | 105.7%
| Appearance Inspection | 35 | 35 | 0 | 0 |  | 0 | 100% | 100%
| QA COB IPQC | 35 | 32 | 3 | 0 |  | 0 | 100% | 100%
| Burn-in Before Test | 32 | 26 | 6 | 0 |  | 0 | 100% | 100%
| COB Burn-In 1 | 26 | 26 | 0 | 0 |  | 0 | 100% | 100%
| Burn-in Pre Test | 26 | 26 | 0 | 0 |  | 0 | 100% | 100%
| COB Burn-In 2 | 26 | 26 | 0 | 0 |  | 0 | 100% | 100%
| Burn-in Post Test | 26 | 26 | 0 | 0 |  | 0 | 100% | 100%
| Lens Coupling | 26 | 26 | 0 | 0 |  | 0 | 100% | 100%
| UV Curing | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| DP-190 | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| BF-4 | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| Baking BF-4 | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| COB Inspection | #REF! | #REF! | #REF! | 9 |  | 9 | #REF! | #REF!
| QA COB OQC | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| INVT | #REF! | #REF! | #REF! | 0 |  | 0 | #REF! | #REF!
| Total Volume | #REF! | #REF! | #REF! | 21 |  | 21 | #REF! | #REF!
| Total Yield | 40 | #REF! | #REF! | 21 |  | 21 | #REF! | #REF!
AOC 400G | Start Runcard | 429 | 429 | 0 |  |  | 0 | 100% | 100%
| AOC Assembly All 1 | 429 | 429 | 0 |  |  |  | 100% | 100%
| AOC Assembly All 2 | 429 | 408 | 5 | 16 | 0 | 16 | 92.54% | 96.27%
| AOC Assembly All 3 | 408 | 408 | 0 |  |  |  | 100% | 100%
| AOC Assembly 1 | 408 | 408 | 0 |  |  | 0 | 100% | 100%
| AOC Assembly 2 | 408 | 407 | 1 |  |  | 0 | 100% | 100%
| AOC Assembly 3 | 407 | 407 | 0 |  |  | 0 | 100% | 100%
| AOC Baking | 407 | 404 | 0 | 3 |  | 3 | 98.53% | 99.26%
| AOC 20TC | 389 | 381 | 8 |  |  | 0 | 100% | 100%
| AOC Post Test | 381 | 270 | 51 | 60 |  | 60 | 68.5% | 84.25%
| TCBer Test | 270 | 226 | 38 | 6 |  | 0 | 95.56% | 97.78%
| Symbol Error Test | 226 | 215 | 5 | 6 |  | 0 | 94.69% | 97.35%
| ATS Test | 215 | 178 | 37 |  |  | 0 | 100% | 100%
| Packet Loss Test | 178 | 157 | 21 |  |  | 0 | 100% | 100%
| AOC Inspection | 157 | 132 | 23 | 2 |  | 0 | 97.45% | 98.73%
| INVT PCS | 132 | 118 | 14 |  |  | 0 | 100% | 100%
| AOC Assembly All 1 | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF!
| AOC Assembly All 2 | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF!
| AOC Assembly All 3 | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF!
| Total Volume | 5273 | 4977 | 203 | 93 |  | 79 | 96.47% | 98.44%
| Total Yield | 429 | 118 | 203 | 93 |  | 79 | 53.15% | 59.9%
Assem.
Testing

## AOC 200G(Returned) (hidden)
100G | 200G | 400G |  | AOC
WO | Qty In | Note |  | Start Runcard | AOC Assembly 1 | AOC Assembly 2 | AOC Assembly 3 | AOC Baking | AOC 20TC | AOC Post Test | TCBer Test | Packet Loss Test | AOC Inspection | INVT PCS
120049614 | 30 | 200G | Target Date | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19
|  |  | Actual Date | 2026-02-19
|  |  | WO In/Out | 30
|  |  | Yield | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
120049615 | 30 | 200G | Target Date | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20
|  |  | Actual Date | 2026-02-19
|  |  | WO In/Out | 30
|  |  | Yield | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
120049616 | 30 | 200G | Target Date | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21
|  |  | Actual Date | 2026-02-19
|  |  | WO In/Out | 30
|  |  | Yield | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
120049617 | 30 | 200G | Target Date | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23
Actual Date
|  |  | WO In/Out | 30
|  |  | Yield | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Formulas:
AOC Assembly 1 = WORKDAY.INTL([Start Runcard],0,11)
AOC Assembly 2 = WORKDAY.INTL([AOC Assembly 1],0,11)
AOC Assembly 3 = WORKDAY.INTL([AOC Assembly 2],0,11)
AOC Baking = WORKDAY.INTL([AOC Assembly 3],0,11)
AOC 20TC = WORKDAY.INTL([AOC Baking],0,11)
AOC Post Test = WORKDAY.INTL([AOC 20TC],2,11)
TCBer Test = WORKDAY.INTL([AOC Post Test],0,11)
Packet Loss Test = WORKDAY.INTL([TCBer Test],0,11)
AOC Inspection = WORKDAY.INTL([Packet Loss Test],0,11)
INVT PCS = WORKDAY.INTL([AOC Inspection],0,11)
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9067260100001 9067260100002 9067260100008
Note on X5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 in repair: 9067260100012
Note on R9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9067260100001 9067260100002 9067260100008
Note on X9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 in repair: 9067260100012
Note on R13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9067260100001 9067260100002 9067260100008
Note on X13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 in repair: 9067260100012
Note on R17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 fails 9067260100001 9067260100002 9067260100008
Note on X17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 in repair: 9067260100012